## Error list
Sl No | Date | Issue | Priority | Status
1 | 2025-10-28 | White space before open parenthesis leads to swara being not recognized and treated as mantra text | P3 | Closed
2 | 2025-10-28 | No white space after close parenthesis leads to mantra text string to be skipped. | P3 | Closed
3 | 2025-10-28 | For each mantra text character with a swara, trailing and leading set of whitespaces is being generated. No trailing or leading whitespaces should be generated so that a contiguous text string will be generated for a passage which should be chanted in one breath | P1 | Closed
4 | 2025-10-28 | Try to make the mantra text bigger and more clear (color and font size). Color: Black, font : Adishila Regular 18 pt ? For the swara, try to have a smaller font in red for online reading and bold black for print | P2 | Closed
5 | 2025-10-28 | Many long mantra texts are cut and the pagination does not have the appropriate margins (left/right) | P1 | Closed
6 | 2025-10-28 | Kandah title and numbers should be inserted | P3 | Closed
7 | 2025-10-28 | Samam numbers should be inserted | P3 | Closed
8 | 2025-10-28 | Ladybug icon to be removed from pdf | P3 | Closed

## Task list
Sl No | What? | Due Date | Owner
1 | Rik - Agneyam to be completed | 2025-10-29 | Shailesh
2 | Rik - Tadvam | 2025-11-02 | Shailesh
3 | Vibhakti corrections to be done | 2025-11-15 | Shailesh
4 | Domain name reservation |  | Sekhar
5 | Aaranam work - how to proceed? Should we drop the swara in parenthesis and have the mantra text quality improved by using OCR?